## High level calendar
TSC final report key milestones - DRAFT | 2020 |  |  |  | 2021
| Sept | Oct | Nov | Dec
Final Report
First draft chapter(s) submitted to staff and other commissioners |  | 2020-10-01
All draft chapters and appendices submitted |  |  | 2020-11-02
Consensus on findings and recommendations |  |  | 2020-11-09
Draft report shared with JFO and Tax |  |  | 2020-11-16
Charts and graphs complete |  |  |  | 2020-12-16
Draft shared with stakeholders |  |  |  | 2020-12-18
Copyediting complete |  |  |  |  | 2020-01-13
Submit |  |  |  |  | 2019-01-15

## Details of actions & mtg goals
| Day of Week | Date | Step | Status
DRAFT DATES (subject to change) | Friday | 2020-09-11 | Commissioners finish filling in google doc areas that each will be responsible for (col F), what additional testimony, research, analysis, etc. is needed for each section (col E&G), fallback plan if certain elements can't be obtained by needed date, and target date to share with other commissioners and staff (col H) | Most, but not all, chapters claimed. Decision on remaining items TBD for after initial chapters.
| Monday | 2020-09-14 | 90 min commissioner discussion on education finance -- 20 min to review and revise this draft timeline and google doc, prioritize needed items, flesh out contingencies, and determine if anything can/should be cut | Done
| Monday | 2020-09-28 | Testimony from Lauren-Glenn Davitian (PEGS), Lori Smith (VT Futures report). Commissioner discussion on their chapters in progress. | Done
| Thursday | 2020-10-01 | Commissioners each submit one draft chapter | Multiple chapters submitted
| Monday | 2020-10-12 | Commissioner discussion to share feedback on initial chapters, address questions or alignment needs that arise, assign work, and modify/adopt guidelines for remaining chapters (if necessary). Revisit remaining chapters, whether to combine or cut, who will take lead, what is needed, etc. | Done
| Monday | 2020-10-22 | Commissioner discussion to share feedback on initial chapters, address questions or alignment needs that arise, assign work, and modify/adopt guidelines for remaining chapters (if necessary). Revisit remaining chapters, whether to combine or cut, who will take lead, what is needed, etc. | Discussion and feedback on income and consumption. Still need to address education and other chapters
| Monday | 2020-11-02 | Revisions to three aforementioned chapters and initial drafts of all remaining chapters shared with staff and other commissioners (Staff to compile unfactchecked version by end of week - 11/6) | Yes to three core chapters and obsolete tax chapter. Timeline on other chapters pushed back, targeting 12/18 stakeholder review rather than JFO/Tax review
| Monday | 2020-11-09 | Meet to reach consensus on messages/themes/recommendations, adopt edits if needed to be supported by other commissioners, determine/prioritize areas that need further work/development | Edits to three core chapters discussed. Other items to discuss in 11/23 meeting
| Monday | 2020-11-16 | Draft sent to JFO and Tax for review (response requested by 12/1) and for staff factchecking and style formatting. | Draft compiled, format agreed upon by TSC, and sent for review on 11/17. TSC agreed not to touch style formatting - leave to individual commissioners. Further discuss factchecking process in 11/23 meeting.
| Monday | 2020-12-07 | Meet to discuss any feedback from staff factchecking and JFO/Tax review; determine implications for findings and recommendations; assign edits and modifications to make by end of week (12/11)
| Monday | 2020-12-14 | Meet to review edits made by Friday; determine what/if any additional work is needed before sharing with stakeholders
| Wednesday | 2020-12-16 | Charts and graphs complete
| Friday | 2020-12-18 | Share draft with other stakeholders (request feedback by 12/31)
| Monday | 2021-01-04 | Meet to discuss any additional feedback - implications for findings and recommendations
| Monday | 2021-01-11 | Meet to address any final edits/unresolved items - finalize report, with remaining days for final copyediting and stakeholder announcement/press release, if any (Report is due Friday the 15th)
This draft sees the key steps of the report-writing process as:
*Writing the agreed-upon chapters, per TSC's "From outline to report" spreadsheet
*Reaching commissioner agreement on the contents and presentation of findings/recommendations, including overarching themes and/or recommendations
*Factchecking and citations
*Review by JFO, Tax, and other stakeholders
*Data presentation, including charts and graphs
*Copyediting, including consistent style and formatting
Key:
Yellow- Commissioners to submit by this date
Blue - Meeting
Green - Other